## Sheet1
Sprint | Date | Feature | Task No. | Task Detail | Task status
Note_App_Sprint 1 | 16/2/2024 | Project UI | TSK-NO-1 | UI Design WireFrame | Done
|  | Project setup | TSK-NO-2 | Environmental Setup | Done
|  |  | TSK-NO-3 | Database Schema | Done
| 17/2/2024 | Sign In | TSK-NO-4 | API | Done
|  | Sign Up | TSK-NO-5 | UI for Sign In/Sign Up | Done
|  |  | TSK-NO-6 | JWT token integration | Done
| 18/2/2024 | View and add notes | TSK-NO-7 | API | Done
|  |  | TSK-NO-8 | UI for add and view notes | Done
|  |  | TSK-NO-9 | Unit Testing | Done
| 19/2/2024 | Access control | TSK-NO-10 | API | Done
|  |  | TSK-NO-11 | Unit Testing | Done